## Backlog
ID | Phase | Workstream | Task | Deliverable / acceptance | Priority | Owner | Dependency | Estimate | Status
FND-001 | 0 — Foundation | Repository | Create GitHub repository and branch protection | Main branch protected; PR checks required | P0 | Tech lead |  | 0.5 day | Not started
FND-002 | 0 — Foundation | Environment | Create dev/staging/prod environment plan | Secrets and URLs separated by environment | P0 | Tech lead | FND-001 | 1 day | Not started
DB-001 | 1 — Data | Supabase | Apply schema migrations | All tables, enums, constraints, indexes, triggers created | P0 | Backend | FND-002 | 1 day | Not started
DB-002 | 1 — Data | Security | Test row-level security by role | Anonymous, customer, staff, manager, admin tests pass | P0 | Backend | DB-001 | 2 days | Not started
AUTH-001 | 2 — Accounts | Authentication | Connect sign-up, sign-in, email confirmation, sign-out | Customer account works end to end | P0 | Full stack | DB-001 | 2 days | Not started
AUTH-002 | 2 — Accounts | Authorization | Admin navigation and route guards | Only staff roles can access /admin | P0 | Full stack | DB-002,AUTH-001 | 1 day | Not started
CAT-001 | 3 — Catalog | Products | Persist product and variant create/edit | Product, SKU, price, cost, tax, status persist | P0 | Full stack | AUTH-002 | 3 days | Not started
CAT-002 | 3 — Catalog | Categories | Persist category tree and sort order | Storefront dropdown reflects admin changes | P0 | Full stack | CAT-001 | 2 days | Not started
MED-001 | 3 — Catalog | Cloudflare R2 | Complete signed image upload flow | JPEG/PNG/WebP/AVIF uploaded; max 10 enforced | P0 | Backend | CAT-001 | 2 days | Not started
MED-002 | 3 — Catalog | Cloudflare Stream | Direct video upload and webhook status | Video ready state and playback URL synchronized | P1 | Backend | CAT-001 | 3 days | Not started
INV-001 | 4 — Inventory | Inventory ledger | Implement receiving, adjustment, reservation, sale, return | Every balance change has an immutable movement | P0 | Backend | DB-002,CAT-001 | 4 days | Not started
INV-002 | 4 — Inventory | Admin UI | Inventory detail/search/sort/filter/export | Search by name/SKU/category; category and location filters | P0 | Full stack | INV-001 | 3 days | Not started
IMP-001 | 4 — Inventory | Excel import | Implement preview and transactional commit | Valid rows commit atomically; errors do not partially write | P0 | Backend | CAT-001,INV-001 | 4 days | Not started
CUS-001 | 5 — Customers | Customer master | Guest, retail, wholesale profiles | Searchable profiles with price level and balances | P0 | Full stack | AUTH-001 | 3 days | Not started
TAX-001 | 5 — Customers | Exemption workflow | Document metadata and approval audit | Tax exemption cannot be self-approved by customer | P0 | Backend | CUS-001 | 3 days | Not started
SAL-001 | 6 — Sales | Orders | Create admin/storefront sales order workflow | Line snapshots, totals, status transitions, stock reservations | P0 | Full stack | INV-001,CUS-001 | 5 days | Not started
SAL-002 | 6 — Sales | Invoices | Issue invoice and PDF/print view | Sequential number, line snapshots, tax, balance | P0 | Full stack | SAL-001 | 4 days | Not started
PAY-001 | 7 — Payments | Payments | Select provider and implement checkout/webhooks | Idempotent payment and refund reconciliation | P1 | Full stack | SAL-002 | 6 days | Deferred
REP-001 | 8 — Reporting | Financial reports | Monthly/yearly sales, received, COGS, expenses, profit | Definitions documented and totals reconcile | P0 | Backend | SAL-002,INV-001 | 4 days | Not started
QA-001 | 9 — Launch | Quality | Accessibility, responsive, security, performance tests | Acceptance checklist completed | P0 | QA | All | 5 days | Not started
OPS-001 | 9 — Launch | Operations | Backups, monitoring, alerts, incident runbook | Restore test and owner alerts verified | P0 | DevOps | DB-001 | 3 days | Not started